## Sheet1
Junk art
Week | Days | Task | Complete | Weight
1 | 2 | Research existing physics games
1 | 2 | Research existing board game adaptaions & platforms | 2023-10-15
2 | 2 | Evaluate existing products | 2023-10-16
2 | 2 | Create pitch video | 2023-10-17
2 | 0.1 | Topic 1 checklist | 2023-10-17 | 0.5
3 | 4 | Extend background research | 2023-10-21
4 | 2 | Extend evaluations | 2023-10-23
4 | 2 | Create proposal video | 2023-10-27
4 | 0.1 | Topic 2 checklist | 2023-10-29 | 0.5
4 | 0.1 | Submit project proposal (Nov 6) | 2023-10-29 | 0
6 | 0.1 | Topic 3 checklist | 2023-11-19 | 0.5
8 | 0.1 | Topic 4 checklist | 2023-12-01 | 0.5
10 | 0.1 | Topic 5 checklist | 2023-12-20 | 0.5
10 | 0.1 | Submit preliminary report (Jan 8) | 2023-12-20 | 10
12 | 0.1 | Topic 6 checklist | 2023-01-01 | 0.5
14 | 0.1 | Topic 7 checklist | 2023-01-08 | 0.5
16 | 0.1 | Topic 8 checklist (Jan 29) |  | 0.5
18 | 0.1 | Topic 9 checklist (Feb 12) |  | 0.5
19 | 0.1 | Submit draft report (Feb 12) |  | 0
20 | 0.1 | Topic 10 checklist (Feb 26) |  | 0.5
22 | 0.1 | Submit final report (Mar 11) |  | 60
22 | 0.1 | Submit video (Mar 11) |  | 5
22 | 1 | Exam |  | 20