## Gantt Chart w % Complete
Build better gantt charts with TeamGantt for FREE!
* = an automatically calculated cell
| TASK NAME | START DATE | DAY OF MONTH* | END DATE | DURATION* (WORK DAYS) | DAYS COMPLETE* | DAYS REMAINING* | TEAM MEMBER | PERCENT COMPLETE | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4
First Sample Project
| Write Landing Page Copy | 2018-01-05 | 5 | 2018-01-08 | 4 | 4 | 0 | Nathan | 100%
| Approve Page Copy | 2018-01-08 | 8 | 2018-01-11 | 4 | 3.2 | 0.8 | Meredith | 80%
| Review Landing Page Design | 2018-01-11 | 11 | 2018-01-16 | 6 | 3.6 | 2.4 | Brandon | 60%
| Build Landing Page | 2018-01-14 | 14 | 2018-01-19 | 6 | 2.4 | 3.6 | Michael | 40%
| Code Review Landing Page | 2018-01-17 | 17 | 2018-01-23 | 7 | 1.4 | 5.6 | Rachel | 20%
Second Sample Project
| Write Promotional Email | 2018-01-09 | 9 | 2018-01-12 | 4 | 4 | 0 | Nathan | 100%
| Design Promotional Email | 2018-01-12 | 12 | 2018-01-19 | 8 | 6.4 | 1.6 | Meredith | 80%
| Send Promotional Email | 2018-01-17 | 17 | 2018-01-19 | 3 | 1.8 | 1.2 | Brandon | 60%
| Analyze Campaign Results | 2018-01-22 | 22 | 2018-01-26 | 5 | 2 | 3 | Michael | 40%
Third Sample Project
| Plan Agenda for Meeting | 2018-01-15 | 15 | 2018-01-19 | 5 | 5 | 0 | Nathan | 100%
| Reserve Room | 2018-01-22 | 22 | 2018-01-23 | 2 | 1.6 | 0.4 | Meredith | 80%
| Finalize Presentation | 2018-01-22 | 22 | 2018-01-26 | 5 | 3 | 2 | Brandon | 60%
| Approve Presentation | 2018-01-26 | 26 | 2018-01-29 | 4 | 1.6 | 2.4 | Michael | 40%
| Create Invitations | 2018-01-22 | 22 | 2018-01-25 | 4 | 0.8 | 3.2 | Rachel | 20%
Fourth Sample Project
| Rewrite Online Calculator | 2018-01-15 | 15 | 2018-01-24 | 10 | 10 | 0 | Nathan | 100%
| Code Review Calculator | 2018-01-25 | 25 | 2018-01-30 | 6 | 4.8 | 1.2 | Meredith | 80%
| Update Messaging | 2018-01-24 | 24 | 2018-01-30 | 7 | 4.2 | 2.8 | Michael | 60%
| Publish Calculator | 2018-01-30 | 30 | 2018-01-31 | 2 | 0 | 2 | Rachel | 0%
Formulas:
DURATION* (WORK DAYS) = DATEDIF([START DATE],[END DATE],"d")+1

## Basic Gantt Chart
GANTT CHART TEMPLATE
* = an automatically calculated cell
| TASK NAME | START DATE | END DATE | START ON DAY* | DURATION* (WORK DAYS) | TEAM MEMBER | PERCENT COMPLETE | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4
First Sample Project
| Write Landing Page Copy | 2018-01-05 | 2018-01-08 | 0 | 4 | Nathan | 100%
| Approve Page Copy | 2018-01-08 | 2018-01-11 | 3 | 4 | Meredith | 80%
| Review Landing Page Design | 2018-01-11 | 2018-01-16 | 6 | 6 | Brandon | 60%
| Build Landing Page | 2018-01-14 | 2018-01-19 | 9 | 6 | Michael | 40%
| Code Review Landing Page | 2018-01-17 | 2018-01-23 | 12 | 7 | Rachel | 20%
Second Sample Project
| Write Promotional Email | 2018-01-09 | 2018-01-12 | 4 | 4 | Nathan | 100%
| Design Promotional Email | 2018-01-12 | 2018-01-19 | 7 | 8 | Meredith | 80%
| Send Promotional Email | 2018-01-17 | 2018-01-19 | 12 | 3 | Brandon | 60%
| Analyze Campaign Results | 2018-01-22 | 2018-01-26 | 17 | 5 | Michael | 40%
Third Sample Project
| Plan Agenda for Meeting | 2018-01-15 | 2018-01-19 | 10 | 5 | Nathan | 100%
| Reserve Room | 2018-01-22 | 2018-01-23 | 17 | 2 | Meredith | 80%
| Finalize Presentation | 2018-01-22 | 2018-01-26 | 17 | 5 | Brandon | 60%
| Approve Presentation | 2018-01-26 | 2018-01-29 | 21 | 4 | Michael | 40%
| Create Invitations | 2018-01-22 | 2018-01-25 | 17 | 4 | Rachel | 20%
Fourth Sample Project
| Rewrite Online Calculator | 2018-01-15 | 2018-01-24 | 10 | 10 | Nathan | 100%
| Code Review Calculator | 2018-01-25 | 2018-01-30 | 20 | 6 | Meredith | 80%
| Update Messaging | 2018-01-24 | 2018-01-30 | 19 | 7 | Michael | 60%
| Publish Calculator | 2018-01-30 | 2018-01-31 | 25 | 2 | Rachel | 0%
Formulas:
DURATION* (WORK DAYS) = DATEDIF([START DATE],[END DATE],"d")+1

## Manual Chart
CM3070
| TASK NAME | START DATE | END DATE | DAYS | WEEK 3 | [6 empty] | WEEK 4 | [6 empty] | WEEK 5 | [6 empty] | WEEK 6 | [6 empty] | WEEK 7 | [6 empty] | WEEK 8 | [6 empty] | WEEK 9 | [6 empty] | WEEK 10 | [6 empty] | WEEK 11 | [6 empty] | WEEK 12 | [6 empty] | WEEK 13 | [6 empty] | WEEK 14 | [6 empty] | WEEK 15 | [6 empty] | WEEK 16 | [6 empty] | WEEK 17 | [6 empty] | WEEK 18 | [6 empty] | WEEK 19 | [6 empty] | WEEK 20 | [6 empty] | WEEK 21 | [6 empty] | WEEK 22
[5 empty] | Su | M | T | W | Th | F | Sa | Su | M | T | W | Th | F | Sa | Su | M | T | W | Th | F | Sa | Su | M | T | W | Th | F | Sa | Su | M | T | W | Th | F | Sa | Su | M | T | W | Th | F | Sa | Su | M | T | W | Th | F | Sa | Su | M | T | W | Th | F | Sa | Su | M | T | W | Th | F | Sa | Su | M | T | W | Th | F | Sa | Su | M | T | W | Th | F | Sa | Su | M | T | W | Th | F | Sa | Su | M | T | W | Th | F | Sa | Su | M | T | W | Th | F | Sa | Su | M | T | W | Th | F | Sa | Su | M | T | W | Th | F | Sa | Su | M | T | W | Th | F | Sa | Su | M | T | W | Th | F | Sa | Su | M | T | W | Th | F | Sa | Su | M | T | W | Th | F | Sa
Discovery |  |  |  |  | WEEK 12 Su: CHRISTMAS; WEEK 13 Su: NEW YEAR; WEEK 16 Sa: HOLIDAY
| Research domain and users | 2023-10-22 | 2023-10-31 | 10 | bar: WEEK 3 Su to WEEK 4 T; WEEK 14 Su to WEEK 14 M
| Create pitch video | 2023-11-01 | 2023-11-04 | 4 | bar: WEEK 6 Su to WEEK 6 T; WEEK 8 Su to WEEK 8 T; WEEK 10 Su to WEEK 10 T; WEEK 14 Su to WEEK 14 T; WEEK 16 Su to WEEK 16 T; WEEK 18 Su to WEEK 18 T; WEEK 20 Su to WEEK 20 T; WEEK 22 Su to WEEK 22 T
| Research existing work | 2023-11-05 | 2023-11-13 | 9 | bar: WEEK 5 Su to WEEK 6 M; WEEK 14 Su to WEEK 14 M
| Write literature review | 2023-11-14 | 2023-11-18 | 5 | bar: WEEK 6 T to WEEK 6 Sa; WEEK 14 Su to WEEK 14 M
Design
| Create product design | 2023-11-19 | 2023-11-27 | 9 | bar: WEEK 7 Su to WEEK 8 M; WEEK 14 Su to WEEK 14 M
| Create evaluation plan | 2023-11-28 | 2023-12-01 | 4 | bar: WEEK 8 T to WEEK 8 F; WEEK 14 Su to WEEK 14 M
| Create work plan | 2023-10-22 | 2023-12-02 | 3 | bar: WEEK 3 Su to WEEK 3 M; WEEK 8 Sa; WEEK 14 Su to WEEK 14 M
| Develop prototype | 2023-12-03 | 2023-12-13 | 11 | bar: WEEK 9 Su to WEEK 10 W; WEEK 14 Su to WEEK 14 M
| Prototype report | 2023-12-14 | 2023-12-15 | 2 | bar: WEEK 10 Th to WEEK 10 F; WEEK 14 Su to WEEK 14 M
Development
| Basic scene, physics, rendering | 2023-12-17 | 2023-12-20 | 4 | bar: WEEK 11 Su to WEEK 11 W; WEEK 14 Su to WEEK 14 M
| Player controls | 2023-12-21 | 2023-12-30 | 7 | bar: WEEK 11 Th to WEEK 11 Sa; WEEK 12 W to WEEK 12 Sa; WEEK 14 Su to WEEK 14 M
| Custom asset creation (Blender) | 2024-01-02 | 2024-01-08 | 7 | bar: WEEK 13 T to WEEK 14 M
| Collision mesh creation | 2024-01-07 | 2024-01-13 | 7
| Game rules | 2024-01-14 | 2024-01-26 | 13 | bar: WEEK 14 Su to WEEK 14 M; WEEK 15 Su to WEEK 16 F
| Player information displays | 2024-01-29 | 2024-02-06 | 9 | bar: WEEK 14 Su to WEEK 14 M; WEEK 17 M to WEEK 18 T
| Menu | 2024-02-07 | 2024-02-10 | 4 | bar: WEEK 14 Su to WEEK 14 M; WEEK 18 W to WEEK 18 Sa
| Multiplayer | 2024-02-11 | 2024-02-24 | 14 | bar: WEEK 14 Su to WEEK 14 M; WEEK 19 Su to WEEK 20 Sa
| Refinement | 2024-02-25 | 2024-03-02 | 7 | bar: WEEK 14 Su to WEEK 14 M; WEEK 21 Su to WEEK 21 Sa
Testing
| User testing: controls | 2024-01-02 | 2024-01-13 | 12 | bar: WEEK 13 T to WEEK 14 Sa
| User testing: custom assets, physics | 2024-01-14 | 2024-01-26 | 13 | bar: WEEK 14 Su to WEEK 14 M; WEEK 15 Su to WEEK 16 F
| User teting: single player game rules | 2024-01-29 | 2024-02-10 | 13 | bar: WEEK 14 Su to WEEK 14 M; WEEK 17 M to WEEK 18 Sa
| User testing: UI | 2024-02-11 | 2024-02-17 | 7 | bar: WEEK 14 Su to WEEK 14 M; WEEK 19 Su to WEEK 19 Sa
| User testing: multiplayer | 2024-02-18 | 2024-03-02 | 14 | bar: WEEK 14 Su to WEEK 14 M; WEEK 20 Su to WEEK 21 Sa
Report
| Compile preliminary report | 2023-12-16 | 2023-12-16 | 1 | bar: WEEK 10 Sa; WEEK 14 Su to WEEK 14 M
| Compile final report | 2024-03-03 | 2024-03-09 | 7 | bar: WEEK 14 Su to WEEK 14 M