## Sheet1
Junk art
Week | Days | Task | Complete | Weight
1 | 2 | Research existing physics games
1 | 2 | Research existing board game adaptaions & platforms
2 | 2 | Evaluate existing products
2 | 2 | Create pitch video
2 | 0.1 | Topic 1 checklist |  | 0.5
4 | 0.1 | Topic 2 checklist |  | 0.5
4 | 0.1 | Submit project proposal (Nov 6) |  | 0
6 | 0.1 | Topic 3 checklist |  | 0.5
8 | 0.1 | Topic 4 checklist |  | 0.5
10 | 0.1 | Topic 5 checklist |  | 0.5
10 | 0.1 | Submit preliminary report (Jan 8) |  | 10
12 | 0.1 | Topic 6 checklist |  | 0.5
14 | 0.1 | Topic 7 checklist |  | 0.5
16 | 0.1 | Topic 8 checklist |  | 0.5
18 | 0.1 | Topic 9 checklist |  | 0.5
20 | 0.1 | Topic 10 checklist |  | 0.5
22 | 0.1 | Submit final report (Mar 11) |  | 60
22 | 0.1 | Submit video (Mar 11) |  | 5
22 | 1 | Exam |  | 20